## 01_Findings
ID | Evidence / Finding | Interpretation | Decision | Action | Priority | Evidence limitation / note
F01 | Acceptable FCS increased from 86.67% at baseline to 93.33% at follow-up (+6.67 pp). | Food consumption status improved among the 60 surveyed panel households. | Maintain the current outcome-monitoring approach and examine whether the improvement is consistent across key subgroups. | Review FCS results by community and relevant vulnerability characteristics; document groups with weaker results. | Medium | Descriptive before/after evidence. It does not establish that MPCA caused the improvement.
F02 | Mean rCSI decreased from 10.47 to 8.15 (-2.32 points). | Households reported less use of the measured food-related coping strategies at follow-up. | Treat the reduction as a positive outcome signal while checking for communities or groups where coping remains elevated. | Disaggregate rCSI by community and relevant vulnerability characteristics; flag higher-risk groups for programme review. | Medium | Descriptive before/after evidence; no causal attribution.
F03 | Mean monthly per-capita economic capacity increased from 58,731 FCFA to 68,290 FCFA (+9,559 FCFA). | Economic capacity increased in the panel, but adequacy cannot yet be judged against an applicable MEB/SMEB. | Do not classify the result as adequate until the contextual MEB/SMEB is established. | Obtain/validate the applicable contextual MEB/SMEB and then assess the proportion of households at or above the threshold. | High | No contextual MEB/SMEB was established in the simulation; no threshold should be invented.
F04 | 83.33% of eligible households received the full planned transfer (50/60). Six households received a partial amount and four received no transfer. | Outcome indicators improved, but delivery completeness has an operational weakness that can affect programme effectiveness and equity. | Investigate partial and non-receipt cases rather than treating the aggregate transfer rate as sufficient. | Reconcile payment records; classify reasons for the 6 partial and 4 non-receipt cases; assign follow-up and corrective actions. | High | Full-transfer indicator denominator is all 60 eligible households.
F05 | Cash-access success was 94.64% among assisted households (53/56); 5.36% reported access problems (3/56). | The transfer mechanism broadly enabled access, but a small group experienced barriers. | Maintain the transfer mechanism while resolving individual access cases and checking whether barriers are concentrated in particular locations or groups. | Investigate the 3 access-problem cases, classify barrier types, and verify resolution. | Medium | Correct denominator is assisted households (56), consistent with the indicator wording.
F06 | Any MPCA receipt was 93.33% (56/60); four eligible households did not receive the programme transfer. | Non-receipt remains an operational exception requiring explanation and follow-up. | Do not close the transfer cycle without reconciling non-receipt cases. | Trace the 4 non-receipt households through payment/reconciliation records and document resolution or referral. | High | The four non-receipt cases are part of the 60 eligible panel households.
F07 | Several PMP/IPTT indicators cannot be assessed at follow-up because the locked follow-up form did not capture the required variables (delivery timeframe, targeting verification denominator, communication/feedback indicators). | The programme cannot fully judge all planned performance dimensions from the available follow-up dataset. | Record these as measurement gaps rather than inventing values. | For the next measurement cycle, add/restore the required variables and ensure their denominators and timing are defined before data collection. | High | This is a MEAL system/design finding, not an outcome finding.

## Methodology_Notes
Framework | Data → Finding → Interpretation → Decision → Action
Evidence base | Validated baseline/follow-up panel comparison and corrected IPTT.
Unit of analysis | Same 60 households, joined by household_id.
Analysis type | Descriptive before/after comparison; no causal attribution.
Positive FCS direction | Higher acceptable FCS proportion / higher FCS score indicates improvement.
Positive rCSI direction | Lower rCSI indicates improvement.
Economic capacity | Higher monthly per-capita economic capacity indicates improvement, but adequacy requires contextual MEB/SMEB.
Cash access denominator | Assisted households only: 56 households received some MPCA.
Full transfer denominator | All 60 eligible households.
DPro alignment | Findings are used to support interpretation, decision-making and action; measurement gaps are documented rather than filled with invented values.

## LOCK_STATUS
Stage | Status
Stage 09 Findings, Decisions & Actions | AUDITED AND LOCKED - V2
Important | Stage 09 reorganized so findings remain the evidence record, while decisions/actions are managed in a separate action register and dashboard inputs provide the handoff to Stage 10.

## Learning_Note
ID | Learning principle | Application in this portfolio
L01 | Data should drive findings and decisions, not the reverse. | The simulated follow-up outcomes were generated independently of IPTT targets; findings were developed from the validated results.

## Review_Summary
Review result | PASS
Formal findings | 7
Learning notes | 1
Causal attribution | Not permitted; analysis is descriptive before/after.
MEB/SMEB | TBD; contextual threshold required.
Key operational issue | 83.33% full-transfer rate; 6 partial and 4 non-receipt cases.
Cash access | 94.64% successful among 56 assisted households; 5.36% reported problems.
Measurement gaps | Delivery timeframe, targeting verification follow-up denominator, and communication/feedback indicators remain unavailable.
Lock status | STAGE 09.1 AUDITED AND LOCKED

## 02_Decision_Action_Register
Action ID | Finding ID | Evidence / Finding | Decision | Management Action | Responsible Role | Illustrative Timeline | Priority | Status | Follow-up Evidence | Decision Rationale / Note
A01 | F01 | Acceptable FCS increased from 86.67% to 93.33% (+6.67 pp). | Maintain outcome monitoring and examine subgroup consistency. | Review FCS by community and relevant vulnerability characteristics; document groups with weaker results. | MEAL Manager / Programme Manager | Next review cycle | Medium | Open | Disaggregated FCS table and documented programme review | Illustrative management-planning field; exact organizational responsibility/timing should be adapted to context.
A02 | F02 | Mean rCSI decreased from 10.47 to 8.15 (-2.32 points). | Treat the reduction as a positive signal while checking for elevated coping. | Disaggregate rCSI by community and relevant vulnerability characteristics; flag higher-risk groups. | MEAL Manager / Programme Manager | Next review cycle | Medium | Open | Disaggregated rCSI analysis and risk-group review | Illustrative management-planning field.
A03 | F03 | Mean monthly per-capita economic capacity increased from 58,731 to 68,290 FCFA (+9,559 FCFA). | Do not classify adequacy until a contextual MEB/SMEB is established. | Obtain and validate the applicable contextual MEB/SMEB, then calculate the proportion at or above the threshold. | Programme Manager / MEAL Manager | Before next economic-capacity interpretation | High | Open | Validated MEB/SMEB reference and updated indicator calculation | No threshold is invented in this portfolio.
A04 | F04 | 83.33% received the full transfer; 6 were partial and 4 were non-receipts. | Investigate partial and non-receipt cases. | Reconcile payment records and follow up on the 10 incomplete/non-received cases. | Programme / Finance / Payment Provider | Within 5 working days | High | Open | Reconciliation log and documented resolution/referral for each case | Illustrative timeline.
A05 | F05 | 94.64% of 56 assisted households successfully accessed cash; 5.36% reported problems. | Maintain the transfer mechanism while resolving access barriers. | Investigate the 3 access-problem cases and verify resolution. | Programme / MEAL | Within 5 working days | Medium | Open | Case follow-up and resolution record | Denominator is 56 assisted households.
A06 | F06 | 4 eligible households did not receive any MPCA. | Do not close the transfer cycle without reconciling these cases. | Trace the 4 cases and document resolution or referral. | Programme / Finance / Payment Provider | Within 5 working days | High | Open | Case reconciliation and closure/referral evidence | Illustrative timeline.
A07 | F07 | Some planned IPTT indicators could not be assessed because required variables or denominators were missing. | Treat the gaps as measurement issues rather than inventing values. | Restore or define missing delivery-timeframe, targeting-verification and communication/feedback variables, denominators and timing before the next collection. | MEAL Manager / Programme Team | Before next follow-up round | High | Open | Revised questionnaire/PMP and denominator definitions | Illustrative planning field; the exact tool revision should follow organizational procedures.

## 03_Dashboard_Inputs
KPI ID | Indicator | Baseline | Follow-up / Actual | Target | Direction | Status | Change | Finding ID | Decision / Management Message
K01 | Acceptable FCS (%) | 86.67 | 93.33 | 90 | Higher is better | Met | +6.67 pp | F01 | Maintain monitoring; examine subgroup consistency.
K02 | Mean rCSI | 10.47 | 8.15 | 9 | Lower is better | Met | -2.32 | F02 | Continue monitoring; identify groups with elevated coping.
K03 | Mean monthly per-capita economic capacity (FCFA) | 58731 | 68290 |  | Context threshold required | TBD | +9,559 | F03 | Establish contextual MEB/SMEB before judging adequacy.
K04 | Full transfer received (%) |  | 83.33 | 90 | Higher is better | Not met | -6.67 pp | F04 | Investigate partial and non-receipt cases.
K05 | Cash access success among assisted households (%) |  | 94.64 | 90 | Higher is better | Met | +4.64 pp | F05 | Investigate the 3 reported access-problem cases.
K06 | Cash access problems among assisted households (%) |  | 5.36 | 10 | Lower is better | Met | +4.64 pp margin | F05 | Maintain mechanism while resolving barriers.
K07 | Any MPCA receipt among eligible households (%) |  | 93.33 |  | Operational monitoring | Reference | 56/60 | F06 | Reconcile 4 non-receipt cases.
K08 | Delivery timeframe indicator |  |  | 90 | Higher is better | Measurement gap | TBD | F07 | Restore delivery-timeframe measurement before next round.

## 04_Stage_Logic
Stage 09 purpose | Convert validated indicator evidence into findings, management decisions and follow-up actions.
Evidence source | Stage 08 validated baseline/follow-up comparison and corrected IPTT.
Core chain | Indicator result → Finding → Interpretation → Decision → Action → Follow-up evidence
Analysis type | Descriptive before/after; no causal attribution.
Management-use principle | A finding is not complete until its implication for management is made explicit.
Dashboard link | 03_Dashboard_Inputs is the structured handoff from Stage 09 into the Stage 10 dashboard.
Planning note | Responsible roles, timelines and action statuses in the action register are illustrative portfolio planning fields, not observed project facts.