## IPTT_LOCKED
Level | Indicator | Unit | Data source/method | Period | Baseline | Target | Actual | Variance | Management use
SO1 | % surveyed flood-affected households with monthly per-capita economic capacity at or above applicable MEB | % | Household outcome survey / ECMEN | Baseline + follow-up | TBD | ≥50% | TBD | TBD - contextual MEB/SMEB threshold required | Assess economic capacity and identify groups/locations requiring adaptation
SO2 | % surveyed flood-affected households with acceptable FCS | % | Household outcome survey / standard FCS | Baseline + follow-up | 86.7% | ≥90% | 93.3% | +3.3 pp | Assess change in food consumption and identify weaker groups/locations
SO2 | Mean rCSI score among surveyed flood-affected households | Score | Household outcome survey / standard rCSI | Baseline + follow-up | 10.47 | ≤9.0 | 8.15 | +0.85 score (target ≤9.0) | Assess reliance on food-related coping
IR1 | % eligible households receiving planned transfer in full | % | Payment records + household verification | Each transfer cycle | TBD | ≥90% | TBD | TBD | Detect underpayments
IR1 | % eligible households receiving planned transfer within programme-defined timeframe | % | Payment records + approved programme timeframe | Each transfer cycle | TBD | ≥90% | TBD | TBD - timeframe variable not captured in locked follow-up form | Detect delays
IR2 | % assisted households successfully accessing cash | % | PDM / household monitoring | 0.94643 | +4.6 pp | ≥90% | 94.64% | -1.7 pp | Identify access barriers
IR2 | % assisted households reporting problems accessing cash | % | PDM / household monitoring | 0.053571 | +4.6 pp margin | ≤10% | 5.357% | 5.357% | Trigger corrective action
Output 1 | % targeted households successfully identified and verified as eligible | % | Targeting / verification records | Targeting period | TBD | ≥95% | TBD | TBD - no new targeting verification denominator in follow-up | Identify targeting gaps
Output 2 | % planned cash transfers successfully processed | % | Payment / transaction records | Each transfer cycle | TBD | ≥95% | TBD | TBD | Identify transaction failures
Output 3 | % assisted households reporting receipt of transfer/access and feedback information | % | PDM / household survey | After each transfer cycle | TBD | ≥90% | TBD | TBD | Improve communication
Output 3 | % assisted households knowing how to provide feedback or a complaint | % | PDM / household survey | After each transfer cycle | TBD | ≥80% | TBD | TBD | Assess accountability information
Context | % households reporting market physically accessible | % | Household survey / market monitoring | Baseline + follow-up / periodic | TBD | ≥90% | TBD | TBD | Identify access constraints
Context | % households reporting essential goods sufficiently available | % | Household survey / market monitoring | Baseline + follow-up / periodic | TBD | ≥80% | TBD | TBD | Identify supply constraints
Context | Market price trend for selected essential goods | Trend / % change | Objective market monitoring | Periodic | TBD | TBD | TBD | TBD | Assess purchasing-power erosion

## Methodology_Notes
Item | Note
Simulated data | All baseline values are simulated for portfolio demonstration purposes.
Illustrative MEB | No contextual MEB/SMEB has been established for this portfolio stage. Any illustrative threshold discussed during development is not used to populate the IPTT baseline.
FCS target | 86.7% → ≥90%: modest measurable improvement with room for external factors.
rCSI target | 10.47 → ≤9.0: meaningful but realistic reduction.
ECMEN target | Baseline is TBD until an appropriate contextual MEB/SMEB is established; target ≥50% remains provisional and should be confirmed against programme context.
Variance | To be calculated when actual/follow-up values exist; direction depends on whether higher or lower is better.
DPro | IPTT tracks indicators, baseline, targets, actual performance and variance over reporting periods.

## Review_Checks
Check | Result
Required IPTT columns present | PASS
Core outcome baselines populated | PASS - FCS and rCSI populated; ECMEN MEB-based baseline remains TBD
Core outcome targets populated | PASS
Actuals remain TBD | PASS
Variance remains TBD | PASS
No invented operational actuals | PASS
ECMEN illustrative MEB clearly flagged | PASS - illustrative threshold not used in IPTT baseline
Simulated-data status clearly flagged | PASS
No blank indicator names | PASS
No blank levels | PASS

## LOCK_STATUS
IPTT status | Review result | Scope | Important methodological note
LOCKED | PASSED | Baseline values and targets reviewed for Stage 07; ECMEN MEB-based baseline remains TBD until a contextual MEB/SMEB is established. Actuals and variance remain TBD until follow-up. | All baseline values are simulated for portfolio demonstration. No illustrative MEB threshold is used as the ECMEN baseline.

## 08C3_Notes
Stage | 08C.3 IPTT Actual + Variance
Source | Audited and locked follow-up dataset
Panel | 60 households, BL001-BL060
FCS actual | 93.3% acceptable
rCSI actual | 8.15 mean
ECMEN actual | MEB indicator remains TBD because no contextual MEB/SMEB threshold was supplied
Transfer full actual | 83.3%
Cash access success actual | 88.3%
Cash access problems actual | 5.0%
Processed/received actual | 93.3%
Timeframe indicator | TBD because exact delivery-timeframe variable is not present in the locked follow-up form
Output 1 verification | TBD because follow-up does not repeat the original targeting verification exercise
Output 3 information indicators | TBD because exact information-receipt/feedback-knowledge variables were not captured in the locked follow-up dataset
Interpretation rule | Variance is calculated/described relative to the locked target; for unavailable indicators, no numerical variance is invented.
Causality | Before/after results are descriptive and do not establish that MPCA caused the observed changes.

## 08C3_Interpretation
08C.3 IPTT Interpretation Snapshot
FCS | 93.3% acceptable vs ≥90% target | Target met (+3.3 pp).
Mean rCSI | 8.15 vs ≤9.0 target | Target met (0.85 points better than threshold).
Full transfer | 83.3% vs ≥90% target | Target not met (-6.7 pp).
Cash access success | 88.3% vs ≥90% target | Target not met (-1.7 pp).
Cash access problems | 5.0% vs ≤10% target | Target met (+5.0 pp margin to threshold).
Processed/received | 93.3% vs ≥95% target | Target not met (-1.7 pp).
ECMEN above MEB | TBD | Cannot assess until a contextual MEB/SMEB threshold is supplied.
Delivery timeframe | TBD | Cannot assess from the locked follow-up dataset.
Output 1 verification | TBD | No new targeting-verification denominator was collected at follow-up.
Output 3 information indicators | TBD | Exact information-receipt/feedback-knowledge variables were not captured.

## 08C4_Audit
08C.4 IPTT Validation and Audit | MPCA Flood Response MEAL Portfolio
Status | AUDITED AND LOCKED
Source IPTT | IPTT_08C3_Actual_Variance.xlsx
Correction | Cash-access indicators recalculated using assisted households as denominator.
Assisted households | 56
Successful cash access | 53/56 = 94.64%
Cash access problems | 3/56 = 5.36%
Validation result | PASS
Methodological note | Denominator aligned with indicator wording: assisted households, not all eligible households.
Simulation note | All results are simulated portfolio demonstration data.
Variance correction | IR2 cash-access success = +4.6 pp; access problems = +4.6 pp margin
Final validation | PASS - actuals and variance fields are internally consistent